PRAKALP-DRISHTI

PARTH'S MASTER DEFENSE GUIDE: Setu-Varsha (Climate Shock Contagion) & Karya-Dakshata (Agency Simulator)

Team Member: Parth | Assigned Modules: Setu-Varsha (Pillar 4) · Karya-Dakshata (Pillar 5 / Engine 10)
Ministry of Statistics & Programme Implementation (MoSPI) | Smart India Hackathon 2026 (SIH26103)
Target: Complete Module Mastery, Mathematics, Data Provenance & Winning Jury Defense

# 1. Executive Mission & What Your Modules Accomplish

Parth, you hold the physical execution and de-biasing engines of PRAKALP-DRISHTI: 1. SETU-VARSHA: Couples 20-year IMD monsoon rainfall anomalies with a multi-sector supply chain dependency graph (DAG), modeling how working-window contractions create domino delay gridlocks and calculate locked public capital.
2. KARYA-DAKSHATA: Re-prices optimistic agency proposals against their actual 20-year delivery track record, generating True Expected Cost, True Expected Timeline, and a 0–100 Agency Execution Reliability Score.

Your presentation narrative is compelling: 'DPRs assume construction proceeds 12 months a year—we prove that monsoons contract working windows to 4–5 months in high-rainfall states. And when agencies pitch best-case budget fantasies, Karya-Dakshata brings a reality check before a single rupee is sanctioned!'

📌 PARTH'S 30-SECOND ELEVATOR PITCH CORE DEFENSE HOOK: 'Setu-Varsha models the 12-month DPR fallacy and supply-chain domino delay cascades. Karya-Dakshata eliminates contractor optimism bias using empirical delivery multipliers across 2,207 mega-projects!'

# 2. Deep-Dive: SETU-VARSHA (Climate Contagion War Room)

SETU-VARSHA integrates VARSHA-SPEED (Janhavi's engine) and SETU-GRAPH (Amey's engine). It models how weather anomalies propagate through India's infrastructure supply chain.

## 2.1 The 5 Key Equations of SETU-VARSHA

1. Working-Window Compression Formula:
    Adjusted Lost Days = Base Lost Days × [ 1 + (Rainfall Anomaly % / 100) × Elasticity ]
    Effective Working Months = max(3.5, 12 - (Adjusted Lost Days / 30.4375))
    Schedule Stretch Multiplier = 12 / Effective Working Months

2. Remaining Exposure Scaling:
    Remaining Work Months = max(0, (100 - Physical Progress %) / 100) × 24 months
    Direct Weather Delay Shock = Remaining Work Months × (Stretch_simulated - Stretch_baseline)

3. Critical Path Method (CPM) Float Absorption (Max-Plus Algebra):
    Total Float (TF) = Late Start - Early Start
    Free Float (FF) = min(Early Start of Successors - Lead Time) - Early Finish
    Absorbed Delay = min(Weather Delay Shock, Free Float)
    Propagated Delay (Excess) = max(0, Weather Delay Shock - Free Float)
    Only excess delay cascades downstream, attenuated by 15% per hop (0.85 multiplier).

4. Delay-Weighted Locked Capital Calculation:
    Locked Capital (₹ Cr) = Project Revised Cost × min(Excess Delay / 48 months, 1.0)
    Honesty Check: 926 isolated projects carry no dependency edges; they are tallied separately under 'Direct Exposure' rather than 'Contagion'.

5. Permutation Monte Carlo Shapley Criticality (Φ_j):
    Coalition Value v(S) = Sum of capex across reachable descendants of coalition S.
    Over M = 30 permutations, the marginal capital unblocked by project j is accumulated to find the national linchpin.

# 3. Deep-Dive: KARYA-DAKSHATA (Agency Execution Simulator)

Karya-Dakshata evaluates every executing agency with ≥ 2 projects in the 2,207 PAIMANA database, de-biasing optimistic proposals before ministerial approval.

## 3.1 Mathematical De-Biasing Formulas

1. True Expected Cost (De-Biased Budget):
    True Expected Cost (₹ Cr) = Proposed Base Cost × [ 1 + (Agency Avg Cost Overrun % / 100) ]
    Example: ₹500 Cr base proposal with +34.2% historical overrun → True Expected Cost = ₹671 Cr.

2. True Expected Timeline (De-Biased Days):
    True Expected Timeline (Days) = Proposed Base Days + (Agency Avg Delay Months × 30.4375)
    Example: 730 days (2 yrs) claimed with 28.5 months historical delay → True Expected Timeline = 1,597 days (~4.4 yrs).

3. Agency Reliability Score (0 to 100):
    Overrun Penalty = min(Avg Cost Overrun %, 200) / 2.0  [0 to 100]
    Reliability Score = max(0.0, 100.0 - (0.6 × Delay Rate % + 0.4 × Overrun Penalty))
    Tiers: ≥80 High Reliability (Green); 50–79 Moderate Risk (Blue); <50 High Overrun Risk (Red).

4. Dead Capital / Zombie Project Screen:
    Zombie Project Condition: Physical Progress < 20%  AND  Expenditure Spent > ₹100 Crore.

# Winning Jury & Evaluator Combat Guide (Q&A)

❓ Is Setu-Varsha a machine learning forecast or an arithmetic scenario?

💬 It is an empirical scenario projection grounded in physical reality. It couples 20 years of IMD state rainfall departure records with calibrated engineering working-windows, propagating delays through a Directed Acyclic Graph (DAG) using standard Critical Path Method (CPM) float absorption.

❓ Why don't you classify all delayed projects as 'Contagion' in Setu-Varsha?

💬 Because 926 out of 2,207 projects have no downstream dependents (like a standalone district road). A delay there hurts that project, but it is not contagion. We report isolated direct exposure separately from true downstream locked capex to avoid inflating numbers.

❓ Why is Karya-Dakshata necessary if MoSPI already tracks delays?

💬 MoSPI's PAIMANA portal only records delays after they happen (descriptive). Karya-Dakshata is proactive (prescriptive): it intervenes at the pre-sanction DPR approval stage, ensuring the Cabinet never approves an optimistic budget without seeing that agency's empirical historical multiple.

❓ Where did you get the agency delivery records for Karya-Dakshata?

💬 Every metric comes from the official MoSPI PAIMANA database of 2,207 Central Sector mega-projects. We grouped projects by executing agency for every PSU and department with at least 2 projects.

❓ What does the Dead Capital Tracker do?

💬 It scans all 2,207 projects to identify 'Zombie Projects' where more than ₹100 Crore of public funds have been spent but physical progress remains under 20%, alerting the Cabinet to stalled funds.

❓ How does Setu-Varsha model projects that are nearly finished?

💬 We scale weather delays by remaining work: a project at 90% progress is barely exposed to weather washouts, whereas a project at 10% progress absorbs the full weather shock.